## SMaiReport
ENG-RVW version |  |  | 7/2/2017 |  |  |  | PLC process
AR_Report version |  |  | 7/2/2017 |  |  |  | Phase 1 +2 |  | Phase 3+4 Concept - detailed design |  |  | Phase 5+6 Build and Test |  |  |  | Phase 7
ARID | Rank | Problem statement | Owner | 12MD | OHG | MOS | AR Assignment Date | Assignment aging | Assessment | Concept appr'v | Detailed approved | Prototype done | FA ready | ES requested | FAI done | ECO released | AR closed | Target date | Status | Type | Current Age | Open date | Date closed | Estimate age at completion | Issue | EE/ ME/ OE | Past due
000033018 |  | OSP - MES - KT# 750-032992-00, CARD CAGE 6U/84HP X 160/220MM 12 SLOT | NGUYEN, HIEU | NA | NA | NA | [11 empty] | 6/7/2017 | Open | MES | 658 | 9/14/2015 |  | 632 |  | E
000036883 | 3704 | OSP-Obsolescence-PN 710-659411-001 ASSY,TESTED RANDTESCAN UP4 | MAI, SON | 2 | 0 | 0 | [11 empty] | 6/18/2017 | Closed | OBS | 20 | 4/18/2017 |  | 61 |  | E
000033949 | 208 | OSP-Obsolescence-PN 0384073-000 TSTD PCA,LVD-LGHTNG VID DIAG V2,SLX | TRUONG, THI | 18 | 7 | 90.97 | 2016-03-11 | 4 |  | DONE - 3/31/2016 | DONE - 3/31/2016 | NA | DONE - 11/4/2016 |  | DONE - 3/28/17 | 2017-05-25 | 2017-06-01 | 6/7/2017 | Closed | OBS | 443 | 3/7/2016 |  | 457 | PCB | E
000036857 |  | OSP-MES-IOT/ Electron Source Station | NGUYEN, HIEU | NA | NA | NA | [12 empty] | Closed | MES | 23 | 4/15/2017 |  |  |  | EMS
000034094 | 404 | OSP-Obsolescence-PN 730-371063-000 CABLE,SLX,LOCO DRIVER,BP TO STEPPER B/H | TRUONG, THI | 2 | 4 | 24 | 2016-07-05 | 11 |  | DONE - 7/28/2016 | DONE - 8/30/2016 | NA | DONE - 11/4/2016 |  | 2017-09-30 | 2017-11-30 | 2017-12-07 | 12/7/2017 | Open | OBS | 460 | 3/30/2016 |  | 617 | Electro-Mech ASSY | EM
000034381 | 36 | OSP-Obsolescence-PN 705-369707-000 PCB,SCSI DISCNCT,INLINE SINGLE/DIFF CONV | MAI, SON | 5 | 0 | 0 | 2016-05-18 | 1 |  | DONE - 8/31/16 | NA | DONE - 1/23/17 | DONE - 5/1/17 | DONE | 2017-06-01 | 2017-07-27 | 2017-08-03 | 8/4/2017 | Open | OBS | 412 | 5/17/2016 |  | 444 |  | E | Need Update
000034523 | 376 | OSP-Obsolescence-PN 730-371065-000 ASSY,SLX,PRISM DRIVER,BP TO STEPPER B/H | TRUONG, THI | 4 | 6 | 18 | 2016-06-08 | 2 |  | DONE - 7/28/2016 | DONE - 8/30/2016 | NA | DONE - 11/4/2016 |  | 2017-09-30 | 2017-11-30 | 2017-12-07 | 12/7/2017 | Open | OBS | 392 | 6/6/2016 |  | 549 | Electro-Mech ASSY | EM |  | C | computer | drive, mouse, keyboard
000034587 |  | OSP-CIP- I.o.T / Electron Source Station | DUONG, TAM | NA | NA | NA | [11 empty] | 8/31/2017 | Open | CIP | 377 | 6/21/2016 |  | 436 |  | EMS |  | E | Electrical
000034721 | 39 | OSP-Obsolescence-PN 0256402-000 UN-INT,POWER SUPPLY,120V,KLA 9X | NGUYEN, TOANT | 3 | 0 | 0 | 2016-11-25 | 130 | DONE | DONE-1/21/2017 | DONE-2/11/2017 | DONE-2/23/17 | DONE - 3/7/2017 | DONE | DONE - 3/9/2017 | DONE - 5/17/2017 | 2017-06-01 | 8/14/2017 | Open | OBS | 350 | 7/18/2016 |  | 392 | UPS | E | Need Update | M | Mechanical
000034726 | 339 | OSP-Obsolescence-PN 0133120-000 KIT,LCD MONITOR UPG,17" | LO, THANG | 4 | 4 | 12 | 2016-07-25 | 7 |  | DONE - 9/6/2016 | DONE - 9/6/2016 | NA | DONE - 3/21/2017 |  | DONE - 3/22/2017 | DONE - 5/22/2017 | 2017-05-29 | 5/29/2017 | Closed | OBS | 329 | 7/18/2016 |  | 315 | Monitor | EM |  | S | Software
000034412 | 1 | OSP-Obsolescence-PN 0532282-000 DRIVE,3.5IN,4TB,7.2K,SAS,6GBPS | TRUONG, THI | 14 | 0 | 0 | 2016-05-25 | 2 |  | NA | DONE - 6/13/2016 | DONE - 7/14/2016 | DONE - 8/14/2016 |  | DONE - 9/12/2016 | DONE - 2/26/2017 | DONE - 2/28/2017 | 4/7/2017 | Closed | OBS | 290 | 5/23/2016 |  | 319 | Disk | C
000034410 | 49 | OSP-Obsolescence-PN 0261867-000 UN-INT PWR SUPPLY,100V,3000VA,KT 9XI | TRUONG, THI | 1 | 0 | 0 | 2016-05-25 | 2 |  | NA | DONE - 6/13/2016 | DONE - 7/14/2016 | DONE - 11/21/2016 |  | DONE - 1/30/2017 | DONE - 2/8/2017 | DONE - 2/21/17 | 3/22/2017 | Closed | OBS | 276 | 5/23/2016 |  | 303 | UPS | E
000035063 | 405 | SMFG-Obsolescence-PN 0389022-000 ASSY, TSTD, HD, UIC10 | LO, THANG | 1 | 2 | 24 | 2016-11-23 | 76 |  | DONE - 1/10/2017 | DONE - 3/20/2017 | NA | DONE - 4/20/2017 | DONE - 3/16/2017 | DONE - 4/20/2017 | DONE - 5/18/2017 | 2017-05-25 | 5/25/2017 | Closed | OBS | 277 | 9/8/2016 |  | 259 | Disk | C
000035444 |  | OSP-MES-IOT/ Electron Source Station | LO, THANG | NA | NA | NA | [11 empty] | 6/30/2017 | Open | MES | 245 | 10/31/2016 |  | 242 |  | EMS
000034941 | 2644 | OSP-Obsolescence-PN 720-17868-000 ASSY,DONGLE,NT,VARS | NGUYEN, HOANG | 0 | 3 | 999 | 2016-09-28 | 42 |  | DONE-11/17/2016 | DONE-11/17/2016 | NA | NA | DONE-1/3/2017 | NA | DONE-4/7/2017 | 2017-04-14 | 4/14/2017 | Closed | OBS | 233 | 8/17/2016 |  | 240 | Dongle | C
000035512 |  | MES - Creating a wiring diagram for new MACBOX 0634283-000 | MAI, SON | NA | NA | NA | [11 empty] | 5/25/2017 | Closed | MES | 184 | 11/8/2016 |  | 198 |  | E
000035088 | 120 | OSP-Obsolescence-PN 0265735-000 250G, SATA DISK, OP CONSOLE, 6XX | NGUYEN, HIEU | 7 | 4 | 6.86 | 2016-09-28 | 13 |  | 2016-11-21 | 2016-11-21 | NA | 2016-12-02 |  | 2016-12-09 | 2017-01-20 | 2017-02-28 | 2/28/2017 | Closed | OBS | 221 | 9/15/2016 |  | 166 | Disk | C
000034863 | 339 | OSP-Obsolescence-PN 0569769-000 FRU,SYS TSTD,MOTOR AMP ASSY,ES35 | MAI, SON | 1 | 1 | 12 |  |  |  | NA | NA | NA | NA |  | NA | NA | 2017-02-28 | 2/28/2017 | Closed | OBS-TBA | 199 | 8/5/2016 |  | 207
000034794 | 67 | OSP-Obsolescence-PN 0222301-001 FRU,EMI NOISE CANCELLATION UNIT,eS35 | DUONG, TAM | 1 | 0 | 0 | [11 empty] | 1/20/2017 | Closed | OBS | 192 | 7/26/2016 | 1/19/2017 | 178
000035556 | 106 | SMFG-Obsolescence-PN 0081663-005 KIT,FRU,COMPUTER & ACCESSORIES,ECD-2 | NGUYEN, HOANG | 4 | 2 | 6 | 2016-11-10 | 0 |  | DONE-1/22/2017 | 2017-02-26 | NA | NA | NA | NA | NA |  | 4/15/2017 | Closed | OBS | 165 | 11/10/2016 |  | 156 | Dongle
000035109 | 72 | SMFG-Obsolescence-PN 740-689343-000 ASSY,RIGHT CASSETTE NEST XP | NGUYEN, HIEU | 1 | 0 | 0 | [11 empty] | 1/31/2017 | Closed | OBS | 136 | 9/20/2016 | 1/10/2017 | 133
000035627 | 698 | SMFG-Obsolescence-PN 780-17407-000 KIT,CONTROLLER,DUAL ION PUMP,8XXX | NGUYEN, HIEU | 4 | 2 | 135.46 | 2016-11-18 | 0 |  | 2017-02-10 | NA | NA | NA |  | NA | 2017-04-30 | 2017-05-07 | 5/21/2017 | Closed | OBS | 187 | 11/18/2016 |  | 184 | Vacuum
000035709 | 230 | OSP-Obsolescence-PN 0205550-000 ASSY,PCB,ATSB,199DEG | NGUYEN, HIEU | 19 | 5 | 131.79 | 2016-11-30 | 2 |  | 2017-01-04 | 2017-01-04 | NA | NA |  | NA | 2017-04-14 | 2017-05-07 | 5/7/2017 | Changed Owner | OBS | 157 | 11/28/2016 |  | 160 | PCB |  | Need Update
000035743 | 3 | SMFG-Obsolescence-PN 0308014-001 PKG FRU,SHUTTER ASSY,WAFER,SP1-TBI | DUONG, TAM | 29 | 3 | 1.24 | 2016-12-20 | 19 |  | DONE 01/13/17 | DONE 01/13/17 | N/A | DONE - 02/15/17 | DONE - 3/8/2017 | DONE -03/03/17 | 2017-05-17 | 2017-05-24 | 6/29/2017 | Closed | OBS | 207 | 12/1/2016 |  | 210 | Electro-Mech ASSY
000035515 | 752 | OSP-Obsolescence-PN 760-034988-00 ASSY,CHIRP CELL CYL LENS FIELD STOP | MAI, SON | 2 | 1 | 178.62 |  |  |  | NA | NA | NA | NA |  | NA | NA |  | 3/31/2017 | Closed | OBS | 121 | 11/8/2016 |  | 143
000035817 | 534 | OSP-Obsolescence-PN 780-14105-002 KIT,SHIPG,ASSY,CHASS,FCB,LAW PROTECT | LO, THANG | 7 | 1 | 55.43 | 2016-12-22 | 9 |  | DONE - 1/10/2017 | NA | NA | 2017-06-16 |  | 2017-06-30 | 2017-07-30 | 2017-08-07 | 8/24/2017 | Open | OBS | 202 | 12/13/2016 |  | 254 | PCB |  | Need Update
000035377 | 80 | OSP-Obsolescence-PN 229-00775-002 TUB'G,PE .170 ID X 1/4 OD BLK | NGUYEN, TOANT | 200 | 0 | 0 | [11 empty] | 1/3/2017 | Closed | OBS | 101 | 10/25/2016 | 1/19/2017 | 70
000035630 | 3795 | OSP-Obsolescence-PN 0033120-001 PCB,FRU,SYSTEM CONTROLLER 2 | NGUYEN, TOANT | 1 | 0 | 188 | 2017-02-01 | 75 |  | NA | NA | NA | NA |  | NA | NA | DONE - 2/21/17 | 8/3/2017 | Closed | OBS | 101 | 11/18/2016 |  | 258 | PCB
000035629 | 725 | SMFG-Obsolescence-PN 0035650-000 EHEE ASSY,SNGL 300MM FOUP,SP1-EHII | TRUONG, THI | 1 | 0 | 172.62 | 2016-11-18 | 0 |  | NA | DONE - 12/12/2016 | NA | NA |  | NA | DONE - 2/9/2017 | DONE - 2/21/17 | 3/15/2017 | Closed | OBS | 97 | 11/18/2016 |  | 117 | PCB
000035873 | 424 | SMFG-Obsolescence-PN 0030686-000 DUAL 200MM EHEE ASSY,EHII,SP1-TBI | TRUONG, THI | 1 | 2 | 24 | 2017-02-01 | 43 |  | NA | DONE - 1/23/2017 | NA | NA |  | NA | DONE - 2/9/2017 | DONE - 2/21/17 | 3/15/2017 | Closed | OBS | 65 | 12/20/2016 |  | 85 | PCB
000036090 | 104 | OSP-Obsolescence-PN 0212590-000 DRIVE,USB,500Gb Maxtor OneTouch III | NGUYEN, HOANG | 2 | 1 | 6 | 2017-02-01 | 15 |  | NA | NA | NA | NA |  | NA | NA | NA | NA | Changed Owner | OBS | 65 | 1/17/2017 |  | 58 | Disk
000036036 |  | ODC-Managing ODC OBS AR's and sustaining team. | MAI, SON | NA | NA | NA | [12 empty] | Open | ODC | 174 | 1/10/2017
000036421 | 36 | OSP-Obsolescence-PN 810-01591-000 ASSY,CABLE,H/V ELECT SRCE | NGUYEN, TOANT | 1 | 0 | 0 | [7 empty] | 2017-03-12 |  |  |  | 4/26/2017 | Closed | OBS | 38 | 2/24/2017 |  | 61
000036363 | 3 | OSP-Obsolescence-PN 740-372671-000 PKG DSK,RAW,WIDE SCSI,36GB,GIGAPREP SWAP | LO, THANG | 12 | 2 | 2 | [11 empty] | 4/23/2017 | Closed | OBS | 37 | 2/21/2017 |  | 61
000036134 |  | OSP-MES-ODC onsite support | NGUYEN, HIEU | NA | NA | NA | [11 empty] | 7/10/2017 | Open | MES | 161 | 1/23/2017 |  | 168
000036444 | 937 | OSP-Obsolescence-PN 750-344623-000PCB,SERVO AMPLIFIER,MOTOR | MAI, SON | 6 | 2 | 435.54 | [11 empty] | 4/29/2017 | Closed | OBS | 31 | 2/27/2017 |  | 61
000036445 | 326 | OSP-Obsolescence-PN 0034984-001SET,HUBPORT,USB,7 PORT,W/POWER SUPPLY | NGUYEN, HOANG | 2 | 2 | 12 | [11 empty] | 4/29/2017 | Closed | OBS | 31 | 2/27/2017 |  | 61
000036160 | 20 | OSP-Obsolescence-PN 350184 BRG,LINEAR,THK,2RSR9+155L | DUONG, TAM | 2 | 0 | 0 | 2017-03-22 | 56 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2017-05-17 | 2017-05-24 | 6/29/2017 | Closed | OBS | 152 | 1/25/2017 |  | 155
000036270 | 468 | OSP-Obsolescence-PN 0614200-000 FRU KIT,17 INCH LCD,ASET-F5 | NGUYEN, TOANT | 1 | 3 | 36 | 2017-02-15 | 7 |  | NA | DONE- 4/1/17 | 2017-07-07 | 2017-07-17 | NA | 2017-07-24 | 2017-09-18 | 2017-09-25 | 7/6/2017 | Open | OBS | 145 | 2/8/2017 |  | 148 | LCD |  | Attention
000036516 | 693 | SMFG-Obsolescence-PN 784-056013-001 FRU QIC 150 TAPE DRIVE W/PS | MAI, SON | 6 | 1 | 131.33 | [11 empty] | 5/6/2017 | Closed | OBS | 48 | 3/7/2017 |  | 60
000036442 | 28 | OSP-Obsolescence-PN 0140589-000G, COPPER PASS-THRU I/O MODULE | DUONG, TAM | 3 | 0 | 0 | 2017-03-08 | 9 | N/A | N/A | 2017-05-19 | N/A | N/A | 2017-05-14 | 2017-06-09 | 2017-07-09 | 2017-07-15 | 7/15/2017 | Open | OBS | 126 | 2/27/2017 |  | 138 |  |  | Need Update
000036503 | 22 | OSP-Obsolescence-PN 0026366-000 CABLE,KEYENCE,2M TRMTR,PJ-VC2T | NGUYEN, TOANT | 1 | 0 | 0 | 2017-03-08 | 2 | 2017-03-15 | DONE-5/4/2017 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 9/23/2017 | Open | OBS | 119 | 3/6/2017 |  | 201
000036440 | 105 | OSP-Obsolescence-PN 750-381989-000DISK ARRAY,SUN T3,1X9X73G | TRUONG, THI | 4 | 2 | 6 | [11 empty] | 4/29/2017 | Closed | OBS | 24 | 2/27/2017 |  | 61
000036590 | 99 | OSP-Obsolescence-PN 0081663-007 KIT,FRU,COMPUTER & ACCESSORIES,ECD-2 | NGUYEN, HOANG | 4 | 1 | 3 | 2017-03-22 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | 5/16/2017 | Closed | OBS | 38 | 3/17/2017 |  | 60
000036299 | 59 | SMFG-Obsolescence-PN 0044208-000KIT, UPGRADE, H2 VL-586 CPU | MAI, SON | 1 | 0 | 0 | [11 empty] | 4/16/2017 | Assigned | OBS-TBA | 16 | 2/14/2017 |  | 61
000036364 | 108 | OSP-Obsolescence-PN 0152723-000 AMPLFR,TRCK,COPLEY,FRU | MAI, SON | 2 | 1 | 6 | [11 empty] | 4/23/2017 | Assigned | OBS-TBA | 16 | 2/21/2017 |  | 61
000036510 | 36 | OSP-Obsolescence-PN 0089335-004 ASSY,INTERLOCK BOX,PHNX | MAI, SON | 3 | 0 | 0 | [11 empty] | 5/6/2017 | Assigned | OBS-TBA | 16 | 3/7/2017 |  | 60
000036423 | 74 | OSP-Obsolescence-PN 470-40158-000 COMPUTER, DELL 2600 FILE SERVER, RANGER | MAI, SON | 1 | 0 | 0 | [11 empty] | 4/26/2017 | Assigned | OBS-TBA | 13 | 2/24/2017 |  | 61
000036630 | 71 | OSP-Obsolescence-PN 065-380208-000CAP PROX SENSOR,10-65VDC,DUAL CONTACTS | MAI, SON | 2 | 0 | 0 | [11 empty] | 5/21/2017 | Assigned | OBS-TBA | 33 | 3/22/2017 |  | 60
000036631 | 68 | OSP-Obsolescence-PN 291-19824-000 SYSTEM WAFER,200MM,W/CONTAINER | MAI, SON | 1 | 0 | 0 | [11 empty] | 5/21/2017 | Assigned | OBS-TBA | 12 | 3/22/2017 |  | 60
000036462 | 65 | OSP-Obsolescence-PN 0335949-000 INDEXER,V1,SMIF | MAI, SON | 1 | 0 | 0 | [11 empty] | 4/30/2017 | Assigned | OBS-TBA | 9 | 2/28/2017 |  | 61
000036511 | 595 | OSP-Obsolescence-PN 0604782-000 FRU,ASSY,TDI ELECTRONICS,HDD+ | MAI, SON | 2 | 0 | 86.31 | [11 empty] | 5/6/2017 | Assigned | OBS-TBA | 9 | 3/7/2017 |  | 60
000036512 | 109 | SMFG-Obsolescence-PN 740-652341-00 ASSY ELEVATOR | MAI, SON | 2 | 1 | 6 | [11 empty] | 5/6/2017 | Assigned | OBS-TBA | 9 | 3/7/2017 |  | 60
000036394 | 16 | OSP-Obsolescence-PN 0032227-000 MAPPER, HAMA, 7" CABLE W 4 PIN CONN | MAI, SON | 14 | 1 | 4.29 | [11 empty] | 4/25/2017 | Assigned | OBS-TBA | 7 | 2/23/2017 |  | 61
000036690 | 55 | OSP-Obsolescence-PN 54-0297 PCA,SERVO FUSE ADAPTER | MAI, SON | 1 | 0 | 0 | [11 empty] | 5/29/2017 | Closed | OBS-TBA | 4 | 3/30/2017 |  | 60
000036508 | 21 | OSP-Obsolescence-PN 0026367-000 CABLE,KEYENCE,2M RCVR,PJ-VC2R | NGUYEN, TOANT | 1 | 0 | 0 | 2017-03-16 | 9 |  | DONE-5/4/2017 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 9/23/2017 | Open | OBS | 118 | 3/7/2017 |  | 200
000036519 | 345 | OSP-Obsolescence-PN 0262225-000FRU KIT,PCB ASSY,TIMING GEN,SP1-TBI | LO, THANG | 5 | 5 | 12 | 2017-03-16 | 9 |  | DONE - 5/4/2017 | NA | NA-EOL | NA-EOL | NA-EOL | NA-EOL | NA-EOL | 2017-07-03 | 7/25/2017 | Open | OBS | 118 | 3/7/2017 |  | 140 |  |  | Attention
000036520 | 91 | OSP-Obsolescence-PN 750-071923-000UN-INT PWR SUPPLY,120V,2200VA,KT 9XI | NGUYEN, TOANT | 3 | 1 | 4 | 2017-03-16 | 9 |  | NA | DONE-5/4/2017 | 2017-06-09 | 2017-06-23 | DONE | 2017-06-28 | 2017-07-26 | 2017-08-02 | 8/2/2017 | Open | OBS | 118 | 3/7/2017 |  | 148 |  |  | Need Update
000036783 | 4 | OSP-Obsolescence-PN 0219545-001 FRU KIT,PWR SUPPLY 5VDC 800AMPS 4KW | MAI, SON | 15 | 3 | 2.4 | [11 empty] | 6/7/2017 | Assigned | OBS-TBA | 17 | 4/7/2017 |  | 61
000036634 |  | OSP-MES-Fan assembly needs to be reverse engineered and documented | NGUYEN, HIEU | NA | NA | NA | [12 empty] | Open | MES | 103 | 3/22/2017
000036882 | 534 | OSP-Obsolescence-PN 0627529-000 PKG FRU ASSY,TSTD PS,IC,SLX | MAI, SON | 10 | 0 | 51.78 | [11 empty] | 6/18/2017 | Assigned | OBS-TBA | 10 | 4/18/2017 |  | 61
000036692 | 101 | OSP-Obsolescence-PN 752-688092-000 POWER SUPPLY,350 WATT | NGUYEN, BAO | 4 | 2 | 6 | 2017-04-07 | 8 | [9 empty] | 9/1/2017 | Open | OBS | 95 | 3/30/2017 |  | 155
000036901 | 51 | OSP-Obsolescence-PN 0249956-000 FRU KIT,PCA,MEASUREMENT CONTROL UV1050 | MAI, SON | 3 | 0 | 0 | [11 empty] | 6/19/2017 | Assigned | OBS-TBA | 9 | 4/19/2017 |  | 61
000036728 | 309 | OSP-Obsolescence-PN 095-386274-000CONTACTOR,AUXILIARY,1NO,FRONT | NGUYEN, HOANG | 1 | 1 | 12 | 2017-04-07 | 4 | DONE- short-term solution approved 5/2/2017 | DONE-5/19/2017 | DONE-5/19/2017 | DONE-5/26/2017 | 2017-06-02 | DONE-4/26/2017 | 2017-06-09 | 2017-07-07 | 2017-07-14 | 7/14/2017 | Open | OBS | 91 | 4/3/2017 |  | 102 |  |  | Need Update
000036903 | 124 | SMFG-Obsolescence-PN 0232670-000 ETHERNET SWTCH,DELL,1GB,48 PORT W/ BRKT | MAI, SON | 12 | 7 | 7 | [11 empty] | 6/19/2017 | Assigned | OBS-TBA | 9 | 4/19/2017 |  | 61
000036782 | 97 | OSP-Obsolescence-PN 0151400-000KIT,P/S REPL PN 070-032763-00 SWS152T | NGUYEN, TOANT | 10 | 4 | 4.8 | 2017-04-17 | 10 |  | DONE - 5/15/17 | NA | NA | 2017-08-15 |  | 2017-09-30 | 2017-11-30 | 2017-12-07 | 12/7/2017 | Open | OBS | 87 | 4/7/2017 |  | 244
000036798 | 35 | OSP-Obsolescence-PN 070-774098-000 POWER SUPPLY,5V,750A,208VAC 3 PHASE | DUONG, TAM | 5 | 0 | 0 | 2017-04-16 | 6 | [9 empty] | 12/27/2017 | Open | OBS | 84 | 4/10/2017 |  | 261
000036884 | 71 | OSP-Obsolescence-PN 0050858-000 FRU,ASSY,FAN MTG PANEL | LO, THANG | 1 | 0 | 0 | 2017-05-03 | 15 | [9 empty] | 10/30/2017 | Open | OBS | 76 | 4/18/2017 |  | 195
000036902 | 76 | OSP-Obsolescence-PN 730-733811-001 CABLE,IMAGE SMB TO IMACS 3 | NGUYEN, TOANT | 1 | 0 | 0 |  |  | DONE- short-term solution approved 4/27 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 8/7/2017 | Open | OBS | 75 | 4/19/2017 |  | 110
000036905 |  | KT Pro - BOM Comparison of SP1-TBI & SP1-DLS | NGUYEN, HIEU | NA | NA | NA | [12 empty] | Closed | KTPRO | 29 | 4/19/2017
000036912 |  | OSP-MES-IOT/ Electron Source Station | PHAN, AN | NA | NA | NA | [12 empty] | Open | MES | 74 | 4/20/2017 |  | 133
000036326 |  | DOC SUPPORT - PN 0652628-000 PKG FRU ASSY,MACBOX,SLX | NGUYEN, TOANT | NA | NA | NA |  |  |  | NA | NA | NA | NA | NA | NA | DONE-5/3/2017 | CLOSED | 5/25/2017 | Closed | DOC | 75 | 2/17/2017 |  | 97
000036913 |  | OSP-MES-IOT/ Electron Source Station | NGUYEN, BAO | NA | NA | NA | [11 empty] | 7/30/2017 | Open | MES | 74 | 4/20/2017 |  | 101
000036959 |  | ODC-Scoping-Redesign-PN 0219545-001 FRU KIT,PWR SUPPLY 5VDC 800AMPS 4KW | NGUYEN, HIEU | NA | NA | NA | [12 empty] | Closed | ODC | 26 | 4/26/2017
000036670 |  | OSP-MES-IOT/ Electron Source Station | TRUONG, THI | NA | NA | NA | [12 empty] | Closed | MES | 36 | 3/28/2017
000036970 | 131 | OSP-Obsolescence-PN 0057977-001 PCB ASSY,CPU 200MHZ MMX,CONFIG,SFS6XX0 | MAI, SON | 21 | 0 | 9.14 | [11 empty] | 6/27/2017 | Assigned | OBS-TBA | 7 | 4/27/2017 |  | 61
000036971 | 44 | OSP-Obsolescence-PN 740-733720-000 ASSY,50/60HZ,IMPELLER,UI,CE,BLAZER | MAI, SON | 1 | 0 | 0 | [11 empty] | 6/27/2017 | Assigned | OBS-TBA | 7 | 4/27/2017 |  | 61
000036972 | 82 | OSP-Obsolescence-PN 0374108-000 ASSY,PDU,2365 | MAI, SON | 1 | 0 | 0 | [11 empty] | 6/27/2017 | Assigned | OBS-TBA | 7 | 4/27/2017 |  | 61
000037003 | 1144 | OSP-Obsolescence-PN 0000845-000 KIT,FRU,FIXED CASSETTE,300MM | MAI, SON | 0 | 0 | 999 | [11 empty] | 7/2/2017 | Assigned | OBS-TBA | 12 | 5/3/2017 |  | 60
000037004 | 110 | OSP-Obsolescence-PN 0260735-000 CBL ASSY,SWE PR CAM ND CTL W/FRT BEAD | MAI, SON | 2 | 1 | 6 | [11 empty] | 7/2/2017 | Assigned | OBS-TBA | 8 | 5/3/2017 |  | 60
000037022 |  | KTS-Transporter's PCAs test fixture | DUONG, TAM | NA | NA | NA | [12 empty] | Open | KTS | 56 | 5/8/2017
000037029 |  | ODC-AR Assignment tracker | NGUYEN, HOANG | NA | NA | NA | [12 empty] | Open | ODC | 56 | 5/8/2017
000037050 | 122 | OSP-Obsolescence-PN 209171 BLOWER 325CFM,230VAC,4 HOSE | NGUYEN, HOANG | 5 | 3 | 7.2 | [11 empty] | 7/8/2017 | Closed | OBS | 48 | 5/9/2017 |  | 60
000037057 |  | OSP-MES-1. To evaluate replacement power supply for 0219545-001;2. To compare the replacement power supplies with the existing model 0219545-0013. Implement the interface adapter, sensing wiring an | NGUYEN, HIEU | NA | NA | NA | [12 empty] | Open | MES | 55 | 5/9/2017
000036859 |  | OSP-FAI-PN 0667972-000 RETROFIT KIT,SCSI SE/DIFF CONV,GIGAPREP | NGUYEN, HIEU | NA | NA | NA | [12 empty] | Open | OBS | 77 | 4/17/2017
000037023 |  | KTS-Transporter's PCAs test fixture | NGUYEN, HIEU | NA | NA | NA | [12 empty] | Open | KTS | 56 | 5/8/2017
000037024 |  | KTS-Transporter's PCAs test fixture | NGUYEN, BAO | NA | NA | NA | [12 empty] | Open | KTS | 56 | 5/8/2017
000037076 | 18 | OSP-Obsolescence-PN 131-07706-000 CHAIN,FLEX CABLE | MAI, SON | 1 | 0 | 0 | [11 empty] | 7/11/2017 | Assigned | OBS-TBA | 10 | 5/12/2017 |  | 60
000037077 | 39 | OSP-Obsolescence-PN 0569769-000 FRU,SYS TSTD,MOTOR AMP ASSY,ES35 | NGUYEN, HIEU | 1 | 0 | 0 | [11 empty] | 7/11/2017 | Open | OBS | 52 | 5/12/2017 |  | 60
000037079 | 69 | OSP-Obsolescence-PN 730-371061-000 ASSY,SLX,SAC DRIVER,BP TO STEPPER B/H | LO, THANG | 2 | 0 | 0 | 2017-05-19 | [10 empty] | 11/14/2017 | Open | OBS | 52 | 5/12/2017 |  | 186
000037124 |  | ODC-CAE, focusing on Computational Fluid Dynamics, investigation | PHAN, AN | NA | NA | NA | [12 empty] | Open | ODC | 48 | 5/16/2017
000037132 |  | KTS-PN 0276654-001 FRU ASSY,TSTD PS M31 HOST/NODE | NGUYEN, HIEU | NA | NA | NA | [12 empty] | Closure Requested | KTS | 47 | 5/17/2017
000037144 | 120 | OSP-Obsolescence-PN 0092083-001 KIT UPGRD,PILLAR,SST WTR FTG,AITUV | MAI, SON | 4 | 3 | 9 | [11 empty] | 7/16/2017 | Assigned | OBS-TBA | 7 | 5/17/2017 |  | 60
000037162 |  | switch PN 0002066-000 & header PN 0002156-000 are EOL, need replacements... used in cable assembly 0001011-002 which in turn is used in assy P/N 0000845-000 | LO, THANG | NA | NA | NA | [12 empty] | Closed | MES | 35 | 5/18/2017
000037174 |  | OSP - FAI for KT # 0020042-000, CBL ASSY,STRT/STP/EMO,SP1 DLS | NGUYEN, HIEU | NA | NA | NA | [12 empty] | Open | FAI | 42 | 5/22/2017
000037175 |  | P1 order # 10654932 for KT # 730-333386-000, ASSY,WIRED MOTOR,SAC,COLL,SLX | NGUYEN, HIEU | NA | NA | NA | [12 empty] | Closed | ESC | 17 | 5/22/2017
000037181 | 812 | OSP-Obsolescence-PN 51-0179 STAGE ASSY,SHUTTLE,HANDLER | MAI, SON | 1 | 1 | 200 | [11 empty] | 7/22/2017 | Closed | OBS-TBA | 30 | 5/23/2017 |  | 60
000037182 | 797 | SMFG-Obsolescence-PN 0128546-000 ASSY,FRU,CRATED,IC,PUMA 9000,DELUXE | MAI, SON | 1 | 0 | 188 | [11 empty] | 7/22/2017 | Open | OBS | 41 | 5/23/2017 |  | 60
000037185 | 107 | OSP-Obsolescence-PN 0357521-000 KIT,MONITOR 17 | NGUYEN, HOANG | 2 | 1 | 6 | [11 empty] | 7/22/2017 | Open | OBS | 41 | 5/23/2017 |  | 60
000037234 |  | MES-PN 780-14105-002 KIT,SHIPG,ASSY,CHASS,FCB,LAW PROTECT | NGUYEN, HIEU | NA | NA | NA | [12 empty] | Closed | MES | 17 | 5/29/2017
000037240 | 90 | OSP-Obsolescence-PN 0068036-000 DIODE,1W,355NM,SS | MAI, SON | 4 | 1 | 3 | [11 empty] | 7/28/2017 | Assigned | OBS-TBA | 10 | 5/29/2017 |  | 60
000037311 | 37 | OSP-Obsolescence-PN 710-657952-20 ASSY,TESTED THETA EDGE LAMP PCB (4" SYS) | NGUYEN, TOANT | 2 | 0 | 0 | [11 empty] | 8/7/2017 | Open | OBS | 26 | 6/7/2017 |  | 61
000037383 | 14 | OSP-Obsolescence-PN 0250491-002 RETROFIT KIT,17 INCH LCD MONITOR | NGUYEN, HOANG | 19 | 12 | 7.58 | [11 empty] | 8/15/2017 | Open | OBS | 18 | 6/15/2017 |  | 61
000037384 | 20 | OSP-Obsolescence-PN 0158721-000 PWR SPLY, MOD, 1U, 230V X 12 | LO, THANG | 2 | 0 | 0 | [11 empty] | 8/15/2017 | Open | OBS | 18 | 6/15/2017 |  | 61
000037385 | 63 | OSP-Obsolescence-PN 55-0558-02 CBL ASSY,SVO CRD-SYS INTFC,J11 | NGUYEN, HOANG | 1 | 0 | 0 | [11 empty] | 8/15/2017 | Open | OBS | 18 | 6/15/2017 |  | 61
000037387 | 78 | OSP-Obsolescence-PN 210-07949-000 VALVE,RIGHT ANGLE,NW 16 MANUAL | LO, THANG | 1 | 0 | 0 | [11 empty] | 8/15/2017 | Open | OBS | 18 | 6/15/2017 |  | 61
000037388 | 120 | OSP-Obsolescence-PN 0002062-000 ASSY,ENCL,UNIV.DC PWR SPLY | NGUYEN, TOANT | 7 | 4 | 6.86 | [11 empty] | 8/15/2017 | Open | OBS | 18 | 6/15/2017 |  | 61
000037400 | 41 | SMFG-Obsolescence-PN 760-321660-003 ASSY,SPATIAL FILTER/PRESCANNER | MAI, SON | 2 | 0 | 0 | [11 empty] | 8/16/2017 | Open | OBS | 17 | 6/16/2017 |  | 61
000037401 | 548 | OSP-Obsolescence-PN 0057209-000 ASYST AXYS,VAC HNDLG VAC MANIFOLD | MAI, SON | 3 | 0 | 57.54 | [11 empty] | 8/16/2017 | Assigned | OBS-TBA | 6 | 6/16/2017 |  | 61
000035708 | 538 | OSP-Obsolescence-PN 501972 CBL ASSY,8 SERIAL PORTS,AIT2 | NGUYEN, TOANT | 1 | 4 | 48 | 2016-11-30 | 2 |  | NA | DONE-1/12/2017 | NA | NA | DONE | DONE-1/17/2017 | NA | 2017-05-12 | 5/12/2017 | Closed | OBS | 203 | 11/28/2016 |  | 165 | Cable
000037440 | 2 | SMFG-Obsolescence-PN 780-391907-000 KIT,SLX +5V POWER SYSTEM RETROFIT | MAI, SON | 13 | 1 | 0.92 | [11 empty] | 8/21/2017 | Open | OBS-TBA | 12 | 6/21/2017 |  | 61
000037442 | 796 | SMFG-Obsolescence-PN 0586375-000 PKG FRU,CHASSIS,IC,CPCI RAPIDIO,W/O H | MAI, SON | 1 | 0 | 188 | [11 empty] | 8/21/2017 | Open | OBS-TBA | 12 | 6/21/2017 |  | 61
000037445 | 67 | OSP-Obsolescence-PN 11301397270000 BACKSIDE INIT ROT DISTRIBUTOR | MAI, SON | 2 | 0 | 0 | [11 empty] | 8/21/2017 | Open | OBS-TBA | 12 | 6/21/2017 |  | 61
000037448 | 125 | OSP-Obsolescence-PN 0054603-000 TESTED COMPUTER,23XX IPC,WINDOWS 2000 OS | MAI, SON | 6 | 0 | 8 | [11 empty] | 8/21/2017 | Open | OBS-TBA | 12 | 6/21/2017 |  | 61
000037452 |  | OSP-FAI-KT# 750-032992-00, CARD CAGE 6U/84HP X 160/220MM 12 SLOT | NGUYEN, HIEU | NA | NA | NA | [12 empty] | Open | FAI | 12 | 6/21/2017
000037529 | 123 | OSP-Obsolescence-PN 0062496-001 ASSY,F.O,CH0-7,IMG CMP.TO I/O PNL(CIBO) | MAI, SON | 3 | 2 | 8 | [11 empty] | 8/29/2017 | Open | OBS-TBA | 4 | 6/29/2017 |  | 61
000037549 |  | P2 order # 10663057 for KT # 705-369707-000, PCB,SCSI DISCNCT,INLINE SINGLE/DIFF CONV | NGUYEN, HIEU | NA | NA | NA | [12 empty] | Open |  | 3 | 6/30/2017

## AREmploy
Time Update |  |  |  | 2017-07-03
AR Type | Obs. | KTS | MES | CIP | FAI | KTPRO | Doc. Support | HelpDesk | Escalation | Others | To Be Assigned
Code | OBS | KTS | MES | CIP | FAI | KTPRO | DOC | HD | ESC | OTH | OBS-TBA
MAI, SON | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5
TRUONG, THI | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DUONG, TAM | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LO, THANG | 6 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NGUYEN, HIEU | 2 | 2 | 4 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0
NGUYEN, TOANT | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NGUYEN, HOANG | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
PHAN, AN | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NGUYEN, BAO | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## ARAging
Week# | Finish In 2 Weeks | Overaging | Aging | Monitoring | Time Update
5 | 3 | 1 | 9 | 4 | 2017-02-11
6 | 4 | 1 | 10 | 2 | 2017-02-17
7 | 1 | 0 | 8 | 2 | 2017-02-23
8 | 1 | 0 | 8 | 2 | 2017-03-02
9 | 1 | 1 | 7 | 1 | 2017-03-09
10 | 1 | 1 | 8 | 0 | 2017-03-16
11 | 1 | 1 | 8 | 0 | 2017-03-23
12 | 3 | 1 | 7 | 1 | 2017-03-30
13 | 3 | 2 | 7 | 2 | 2017-04-07
14 | 3 | 2 | 6 | 2 | 2017-04-13
15 | 3 | 2 | 6 | 5 | 2017-04-21
16 | 4 | 2 | 5 | 4 | 2017-04-28
17 | 5 | 2 | 5 | 4 | 2017-05-05
18 | 5 | 2 | 5 | 4 | 2017-05-11
19 | 5 | 3 | 5 | 3 | 2017-05-18
20 | 5 | 2 | 4 | 3 | 2017-05-25
21 | 5 | 2 | 6 | 1 | 2017-06-01
22 | 4 | 3 | 5 | 1 | 2017-06-08
23 | 4 | 3 | 4 | 1 | 2017-06-15
24 | 3 | 3 | 3 | 1 | 2017-06-22
25 | 1 | 3 | 2 | 1 | 2017-06-29
26 | 1 | 3 | 2 | 1 | 2017-07-03

## ARNotice
ENG-RVW version |  |  | 7/2/2017 | Time Update 7/3/2017 |  |  | PLC process
AR_Report version |  |  | 7/2/2017 |  |  |  | Phase 1 +2 |  | Phase 3 Concept | Phase 4 POR | Phase 5+6 Build and Test |  |  | Phase 7 Documentation & Closure
ARID | Rank | Problem statement | Owner | 12MD | OHG | MOS | AR Assignment Date | Assignment aging | Concept appr'v | POR approved | Prototype done | FA ready | FAI done | ECO released | AR closed | Target date | Status | Type | Current Age | Open date | Date closed | Estimate age at completion | Issue | Past due
000034381 | 36 | OSP-Obsolescence-PN 705-369707-000 PCB,SCSI DISCNCT,INLINE SINGLE/DIFF CONV | MAI, SON | 5 | 0 | 0 | 2016-05-18 | 1 | DONE - 8/31/16 |  | DONE - 1/23/17 | DONE - 5/1/17 | 2017-06-01 | 2017-07-27 | 2017-08-03 | 8/4/2017 | Open | OBS | 412 | 5/17/2016 |  | 444 |  | Need Update
000034721 | 39 | OSP-Obsolescence-PN 0256402-000 UN-INT,POWER SUPPLY,120V,KLA 9X | NGUYEN, TOANT | 3 | 0 | 0 | 2016-11-25 | 130 | DONE-1/21/2017 |  | DONE-2/23/17 | DONE - 3/7/2017 | DONE - 3/9/2017 | DONE - 5/17/2017 | 2017-06-01 | 8/14/2017 | Open | OBS | 350 | 7/18/2016 |  | 392 | UPS | Need Update
000035709 | 230 | OSP-Obsolescence-PN 0205550-000 ASSY,PCB,ATSB,199DEG | NGUYEN, HIEU | 19 | 5 | 131.79 | 2016-11-30 | 2 | 2017-01-04 |  | NA | NA | NA | 2017-04-14 | 2017-05-07 | 5/7/2017 | Changed Owner | OBS | 157 | 11/28/2016 |  | 160 | PCB | Need Update
000035817 | 534 | OSP-Obsolescence-PN 780-14105-002 KIT,SHIPG,ASSY,CHASS,FCB,LAW PROTECT | LO, THANG | 7 | 1 | 55.43 | 2016-12-22 | 9 | DONE - 1/10/2017 |  | NA | 2017-06-16 | 2017-06-30 | 2017-07-30 | 2017-08-07 | 8/24/2017 | Open | OBS | 202 | 12/13/2016 |  | 254 | PCB | Need Update
000036270 | 468 | OSP-Obsolescence-PN 0614200-000 FRU KIT,17 INCH LCD,ASET-F5 | NGUYEN, TOANT | 1 | 3 | 36 | 2017-02-15 | 7 | NA |  | 2017-07-07 | 2017-07-17 | 2017-07-24 | 2017-09-18 | 2017-09-25 | 7/6/2017 | Open | OBS | 145 | 2/8/2017 |  | 148 | LCD | Attention
000036442 | 28 | OSP-Obsolescence-PN 0140589-000G, COPPER PASS-THRU I/O MODULE | DUONG, TAM | 3 | 0 | 0 | 2017-03-08 | 9 | N/A |  | N/A | N/A | 2017-06-09 | 2017-07-09 | 2017-07-15 | 7/15/2017 | Open | OBS | 126 | 2/27/2017 |  | 138 |  | Need Update
000036519 | 345 | OSP-Obsolescence-PN 0262225-000FRU KIT,PCB ASSY,TIMING GEN,SP1-TBI | LO, THANG | 5 | 5 | 12 | 2017-03-16 | 9 | DONE - 5/4/2017 |  | NA-EOL | NA-EOL | NA-EOL | NA-EOL | 2017-07-03 | 7/25/2017 | Open | OBS | 118 | 3/7/2017 |  | 140 |  | Attention
000036520 | 91 | OSP-Obsolescence-PN 750-071923-000UN-INT PWR SUPPLY,120V,2200VA,KT 9XI | NGUYEN, TOANT | 3 | 1 | 4 | 2017-03-16 | 9 | NA |  | 2017-06-09 | 2017-06-23 | 2017-06-28 | 2017-07-26 | 2017-08-02 | 8/2/2017 | Open | OBS | 118 | 3/7/2017 |  | 148 |  | Need Update
000036728 | 309 | OSP-Obsolescence-PN 095-386274-000CONTACTOR,AUXILIARY,1NO,FRONT | NGUYEN, HOANG | 1 | 1 | 12 | 2017-04-07 | 4 | DONE-5/19/2017 |  | DONE-5/26/2017 | 2017-06-02 | 2017-06-09 | 2017-07-07 | 2017-07-14 | 7/14/2017 | Open | OBS | 91 | 4/3/2017 |  | 102 |  | Need Update

## ARTrkDateCount
ENG-RVW version |  |  | 7/2/2017 |  |  | RunTime | PLC process
AR_Report version |  |  | 7/2/2017 |  |  | 7/3/2017 | Phase 1 +2 |  | Phase 3+4 Concept - detailed design |  |  | Phase 5+6 Build and Test |  |  |  | Phase 7
ARID | Rank | Problem statement | Owner | 12MD | OHG | MOS | AR Assignment Date | Assignment aging | Assessment | Concept appr'v | Detailed approved | Prototype done | FA ready | ES requested | FAI done | ECO released | AR closed | Target date | Status | Type | Current Age | Open date | Date closed | Estimate age at completion | Issue | EE/ ME/ OE | Past due
000033018 |  | OSP - MES - KT# 750-032992-00, CARD CAGE 6U/84HP X 160/220MM 12 SLOT | NGUYEN, HIEU | NA | NA | NA | [11 empty] | 6/7/2017 | Open | MES | 658 | 9/14/2015 |  | 632 |  | E
000036883 | 3704 | OSP-Obsolescence-PN 710-659411-001 ASSY,TESTED RANDTESCAN UP4 | MAI, SON | 2 | 0 | 0 | [11 empty] | 6/18/2017 | Closed | OBS | 20 | 4/18/2017 |  | 61 |  | E
000033949 | 208 | OSP-Obsolescence-PN 0384073-000 TSTD PCA,LVD-LGHTNG VID DIAG V2,SLX | TRUONG, THI | 18 | 7 | 90.97 | 2016-03-11 | 4 |  | 20 | 0 |  |  |  |  | 58 | 7 | 6/7/2017 | Closed | OBS | 443 | 3/7/2016 |  | 457 | PCB | E
000036857 |  | OSP-MES-IOT/ Electron Source Station | NGUYEN, HIEU | NA | NA | NA | [12 empty] | Closed | MES | 23 | 4/15/2017 |  |  |  | EMS
000034094 | 404 | OSP-Obsolescence-PN 730-371063-000 CABLE,SLX,LOCO DRIVER,BP TO STEPPER B/H | TRUONG, THI | 2 | 4 | 24 | 2016-07-05 | 11 |  | 23 | 33 |  |  |  |  | 61 | 7 | 12/7/2017 | Open | OBS | 460 | 3/30/2016 |  | 617 | Electro-Mech ASSY | EM
000034381 | 36 | OSP-Obsolescence-PN 705-369707-000 PCB,SCSI DISCNCT,INLINE SINGLE/DIFF CONV | MAI, SON | 5 | 0 | 0 | 2016-05-18 | 1 |  | 105 |  |  | 98 |  |  | 56 | 7 | 8/4/2017 | Open | OBS | 412 | 5/17/2016 |  | 444 |  | E | Need Update
000034523 | 376 | OSP-Obsolescence-PN 730-371065-000 ASSY,SLX,PRISM DRIVER,BP TO STEPPER B/H | TRUONG, THI | 4 | 6 | 18 | 2016-06-08 | 2 |  | 50 | 33 |  |  |  |  | 61 | 7 | 12/7/2017 | Open | OBS | 392 | 6/6/2016 |  | 549 | Electro-Mech ASSY | EM |  | C | computer | drive, mouse, keyboard
000034587 |  | OSP-CIP- I.o.T / Electron Source Station | DUONG, TAM | NA | NA | NA | [11 empty] | 8/31/2017 | Open | CIP | 377 | 6/21/2016 |  | 436 |  | EMS |  | E | Electrical
000034721 | 39 | OSP-Obsolescence-PN 0256402-000 UN-INT,POWER SUPPLY,120V,KLA 9X | NGUYEN, TOANT | 3 | 0 | 0 | 2016-11-25 | 130 | DONE | 57 | 21 | 12 | 12 |  |  | 69 | 15 | 8/14/2017 | Open | OBS | 350 | 7/18/2016 |  | 392 | UPS | E | Need Update | M | Mechanical
000034726 | 339 | OSP-Obsolescence-PN 0133120-000 KIT,LCD MONITOR UPG,17" | LO, THANG | 4 | 4 | 12 | 2016-07-25 | 7 |  | 43 | 0 |  |  |  |  | 61 | 7 | 5/29/2017 | Closed | OBS | 329 | 7/18/2016 |  | 315 | Monitor | EM |  | S | Software
000034412 | 1 | OSP-Obsolescence-PN 0532282-000 DRIVE,3.5IN,4TB,7.2K,SAS,6GBPS | TRUONG, THI | 14 | 0 | 0 | 2016-05-25 | 2 |  |  |  | 31 | 31 |  |  | 167 | 2 | 4/7/2017 | Closed | OBS | 290 | 5/23/2016 |  | 319 | Disk | C
000034410 | 49 | OSP-Obsolescence-PN 0261867-000 UN-INT PWR SUPPLY,100V,3000VA,KT 9XI | TRUONG, THI | 1 | 0 | 0 | 2016-05-25 | 2 |  |  |  | 31 | 130 |  |  | 9 | 13 | 3/22/2017 | Closed | OBS | 276 | 5/23/2016 |  | 303 | UPS | E
000035063 | 405 | SMFG-Obsolescence-PN 0389022-000 ASSY, TSTD, HD, UIC10 | LO, THANG | 1 | 2 | 24 | 2016-11-23 | 76 |  | 48 | 69 |  |  | -35 | 35 | 28 | 7 | 5/25/2017 | Closed | OBS | 277 | 9/8/2016 |  | 259 | Disk | C
000035444 |  | OSP-MES-IOT/ Electron Source Station | LO, THANG | NA | NA | NA | [11 empty] | 6/30/2017 | Open | MES | 245 | 10/31/2016 |  | 242 |  | EMS
000034941 | 2644 | OSP-Obsolescence-PN 720-17868-000 ASSY,DONGLE,NT,VARS | NGUYEN, HOANG | 0 | 3 | 999 | 2016-09-28 | 42 |  | 50 | 0 | [5 empty] | 7 | 4/14/2017 | Closed | OBS | 233 | 8/17/2016 |  | 240 | Dongle | C
000035512 |  | MES - Creating a wiring diagram for new MACBOX 0634283-000 | MAI, SON | NA | NA | NA | [11 empty] | 5/25/2017 | Closed | MES | 184 | 11/8/2016 |  | 198 |  | E
000035088 | 120 | OSP-Obsolescence-PN 0265735-000 250G, SATA DISK, OP CONSOLE, 6XX | NGUYEN, HIEU | 7 | 4 | 6.86 | 2016-09-28 | 13 |  | 54 | 0 |  |  |  |  | 42 | 39 | 2/28/2017 | Closed | OBS | 221 | 9/15/2016 |  | 166 | Disk | C
000034863 | 339 | OSP-Obsolescence-PN 0569769-000 FRU,SYS TSTD,MOTOR AMP ASSY,ES35 | MAI, SON | 1 | 1 | 12 | [11 empty] | 2/28/2017 | Closed | OBS-TBA | 199 | 8/5/2016 |  | 207
000034794 | 67 | OSP-Obsolescence-PN 0222301-001 FRU,EMI NOISE CANCELLATION UNIT,eS35 | DUONG, TAM | 1 | 0 | 0 | [11 empty] | 1/20/2017 | Closed | OBS | 192 | 7/26/2016 | 1/19/2017 | 178
000035556 | 106 | SMFG-Obsolescence-PN 0081663-005 KIT,FRU,COMPUTER & ACCESSORIES,ECD-2 | NGUYEN, HOANG | 4 | 2 | 6 | 2016-11-10 | 0 |  | 73 | 35 | [6 empty] | 4/15/2017 | Closed | OBS | 165 | 11/10/2016 |  | 156 | Dongle
000035109 | 72 | SMFG-Obsolescence-PN 740-689343-000 ASSY,RIGHT CASSETTE NEST XP | NGUYEN, HIEU | 1 | 0 | 0 | [11 empty] | 1/31/2017 | Closed | OBS | 136 | 9/20/2016 | 1/10/2017 | 133
000035627 | 698 | SMFG-Obsolescence-PN 780-17407-000 KIT,CONTROLLER,DUAL ION PUMP,8XXX | NGUYEN, HIEU | 4 | 2 | 135.46 | 2016-11-18 | 0 |  | 84 | [6 empty] | 7 | 5/21/2017 | Closed | OBS | 187 | 11/18/2016 |  | 184 | Vacuum
000035709 | 230 | OSP-Obsolescence-PN 0205550-000 ASSY,PCB,ATSB,199DEG | NGUYEN, HIEU | 19 | 5 | 131.79 | 2016-11-30 | 2 |  | 35 | 0 | [5 empty] | 23 | 5/7/2017 | Changed Owner | OBS | 157 | 11/28/2016 |  | 160 | PCB |  | Need Update
000035743 | 3 | SMFG-Obsolescence-PN 0308014-001 PKG FRU,SHUTTER ASSY,WAFER,SP1-TBI | DUONG, TAM | 29 | 3 | 1.24 | 2016-12-20 | 19 |  | 24 | 0 |  |  | 21 | -5 | 75 | 7 | 6/29/2017 | Closed | OBS | 207 | 12/1/2016 |  | 210 | Electro-Mech ASSY
000035515 | 752 | OSP-Obsolescence-PN 760-034988-00 ASSY,CHIRP CELL CYL LENS FIELD STOP | MAI, SON | 2 | 1 | 178.62 | [11 empty] | 3/31/2017 | Closed | OBS | 121 | 11/8/2016 |  | 143
000035817 | 534 | OSP-Obsolescence-PN 780-14105-002 KIT,SHIPG,ASSY,CHASS,FCB,LAW PROTECT | LO, THANG | 7 | 1 | 55.43 | 2016-12-22 | 9 |  | 19 | [5 empty] | 30 | 8 | 8/24/2017 | Open | OBS | 202 | 12/13/2016 |  | 254 | PCB |  | Need Update
000035377 | 80 | OSP-Obsolescence-PN 229-00775-002 TUB'G,PE .170 ID X 1/4 OD BLK | NGUYEN, TOANT | 200 | 0 | 0 | [11 empty] | 1/3/2017 | Closed | OBS | 101 | 10/25/2016 | 1/19/2017 | 70
000035630 | 3795 | OSP-Obsolescence-PN 0033120-001 PCB,FRU,SYSTEM CONTROLLER 2 | NGUYEN, TOANT | 1 | 0 | 188 | 2017-02-01 | 75 | [9 empty] | 8/3/2017 | Closed | OBS | 101 | 11/18/2016 |  | 258 | PCB
000035629 | 725 | SMFG-Obsolescence-PN 0035650-000 EHEE ASSY,SNGL 300MM FOUP,SP1-EHII | TRUONG, THI | 1 | 0 | 172.62 | 2016-11-18 | 0 | [8 empty] | 12 | 3/15/2017 | Closed | OBS | 97 | 11/18/2016 |  | 117 | PCB
000035873 | 424 | SMFG-Obsolescence-PN 0030686-000 DUAL 200MM EHEE ASSY,EHII,SP1-TBI | TRUONG, THI | 1 | 2 | 24 | 2017-02-01 | 43 | [8 empty] | 12 | 3/15/2017 | Closed | OBS | 65 | 12/20/2016 |  | 85 | PCB
000036090 | 104 | OSP-Obsolescence-PN 0212590-000 DRIVE,USB,500Gb Maxtor OneTouch III | NGUYEN, HOANG | 2 | 1 | 6 | 2017-02-01 | 15 | [9 empty] | NA | Changed Owner | OBS | 65 | 1/17/2017 |  | 58 | Disk
000036036 |  | ODC-Managing ODC OBS AR's and sustaining team. | MAI, SON | NA | NA | NA | [12 empty] | Open | ODC | 174 | 1/10/2017
000036421 | 36 | OSP-Obsolescence-PN 810-01591-000 ASSY,CABLE,H/V ELECT SRCE | NGUYEN, TOANT | 1 | 0 | 0 | [11 empty] | 4/26/2017 | Closed | OBS | 38 | 2/24/2017 |  | 61
000036363 | 3 | OSP-Obsolescence-PN 740-372671-000 PKG DSK,RAW,WIDE SCSI,36GB,GIGAPREP SWAP | LO, THANG | 12 | 2 | 2 | [11 empty] | 4/23/2017 | Closed | OBS | 37 | 2/21/2017 |  | 61
000036134 |  | OSP-MES-ODC onsite support | NGUYEN, HIEU | NA | NA | NA | [11 empty] | 7/10/2017 | Open | MES | 161 | 1/23/2017 |  | 168
000036444 | 937 | OSP-Obsolescence-PN 750-344623-000PCB,SERVO AMPLIFIER,MOTOR | MAI, SON | 6 | 2 | 435.54 | [11 empty] | 4/29/2017 | Closed | OBS | 31 | 2/27/2017 |  | 61
000036445 | 326 | OSP-Obsolescence-PN 0034984-001SET,HUBPORT,USB,7 PORT,W/POWER SUPPLY | NGUYEN, HOANG | 2 | 2 | 12 | [11 empty] | 4/29/2017 | Closed | OBS | 31 | 2/27/2017 |  | 61
000036160 | 20 | OSP-Obsolescence-PN 350184 BRG,LINEAR,THK,2RSR9+155L | DUONG, TAM | 2 | 0 | 0 | 2017-03-22 | 56 | [8 empty] | 7 | 6/29/2017 | Closed | OBS | 152 | 1/25/2017 |  | 155
000036270 | 468 | OSP-Obsolescence-PN 0614200-000 FRU KIT,17 INCH LCD,ASET-F5 | NGUYEN, TOANT | 1 | 3 | 36 | 2017-02-15 | 7 |  |  |  | 97 | 10 |  |  | 56 | 7 | 7/6/2017 | Open | OBS | 145 | 2/8/2017 |  | 148 | LCD |  | Attention
000036516 | 693 | SMFG-Obsolescence-PN 784-056013-001 FRU QIC 150 TAPE DRIVE W/PS | MAI, SON | 6 | 1 | 131.33 | [11 empty] | 5/6/2017 | Closed | OBS | 48 | 3/7/2017 |  | 60
000036442 | 28 | OSP-Obsolescence-PN 0140589-000G, COPPER PASS-THRU I/O MODULE | DUONG, TAM | 3 | 0 | 0 | 2017-03-08 | 9 | N/A | [5 empty] | 26 | 30 | 6 | 7/15/2017 | Open | OBS | 126 | 2/27/2017 |  | 138 |  |  | Need Update
000036503 | 22 | OSP-Obsolescence-PN 0026366-000 CABLE,KEYENCE,2M TRMTR,PJ-VC2T | NGUYEN, TOANT | 1 | 0 | 0 | 2017-03-08 | 2 | 2017-03-15 | 57 | [7 empty] | 9/23/2017 | Open | OBS | 119 | 3/6/2017 |  | 201
000036440 | 105 | OSP-Obsolescence-PN 750-381989-000DISK ARRAY,SUN T3,1X9X73G | TRUONG, THI | 4 | 2 | 6 | [11 empty] | 4/29/2017 | Closed | OBS | 24 | 2/27/2017 |  | 61
000036590 | 99 | OSP-Obsolescence-PN 0081663-007 KIT,FRU,COMPUTER & ACCESSORIES,ECD-2 | NGUYEN, HOANG | 4 | 1 | 3 | 2017-03-22 |  | NA | [8 empty] | 5/16/2017 | Closed | OBS | 38 | 3/17/2017 |  | 60
000036299 | 59 | SMFG-Obsolescence-PN 0044208-000KIT, UPGRADE, H2 VL-586 CPU | MAI, SON | 1 | 0 | 0 | [11 empty] | 4/16/2017 | Assigned | OBS-TBA | 16 | 2/14/2017 |  | 61
000036364 | 108 | OSP-Obsolescence-PN 0152723-000 AMPLFR,TRCK,COPLEY,FRU | MAI, SON | 2 | 1 | 6 | [11 empty] | 4/23/2017 | Assigned | OBS-TBA | 16 | 2/21/2017 |  | 61
000036510 | 36 | OSP-Obsolescence-PN 0089335-004 ASSY,INTERLOCK BOX,PHNX | MAI, SON | 3 | 0 | 0 | [11 empty] | 5/6/2017 | Assigned | OBS-TBA | 16 | 3/7/2017 |  | 60
000036423 | 74 | OSP-Obsolescence-PN 470-40158-000 COMPUTER, DELL 2600 FILE SERVER, RANGER | MAI, SON | 1 | 0 | 0 | [11 empty] | 4/26/2017 | Assigned | OBS-TBA | 13 | 2/24/2017 |  | 61
000036630 | 71 | OSP-Obsolescence-PN 065-380208-000CAP PROX SENSOR,10-65VDC,DUAL CONTACTS | MAI, SON | 2 | 0 | 0 | [11 empty] | 5/21/2017 | Assigned | OBS-TBA | 33 | 3/22/2017 |  | 60
000036631 | 68 | OSP-Obsolescence-PN 291-19824-000 SYSTEM WAFER,200MM,W/CONTAINER | MAI, SON | 1 | 0 | 0 | [11 empty] | 5/21/2017 | Assigned | OBS-TBA | 12 | 3/22/2017 |  | 60
000036462 | 65 | OSP-Obsolescence-PN 0335949-000 INDEXER,V1,SMIF | MAI, SON | 1 | 0 | 0 | [11 empty] | 4/30/2017 | Assigned | OBS-TBA | 9 | 2/28/2017 |  | 61
000036511 | 595 | OSP-Obsolescence-PN 0604782-000 FRU,ASSY,TDI ELECTRONICS,HDD+ | MAI, SON | 2 | 0 | 86.31 | [11 empty] | 5/6/2017 | Assigned | OBS-TBA | 9 | 3/7/2017 |  | 60
000036512 | 109 | SMFG-Obsolescence-PN 740-652341-00 ASSY ELEVATOR | MAI, SON | 2 | 1 | 6 | [11 empty] | 5/6/2017 | Assigned | OBS-TBA | 9 | 3/7/2017 |  | 60
000036394 | 16 | OSP-Obsolescence-PN 0032227-000 MAPPER, HAMA, 7" CABLE W 4 PIN CONN | MAI, SON | 14 | 1 | 4.29 | [11 empty] | 4/25/2017 | Assigned | OBS-TBA | 7 | 2/23/2017 |  | 61
000036690 | 55 | OSP-Obsolescence-PN 54-0297 PCA,SERVO FUSE ADAPTER | MAI, SON | 1 | 0 | 0 | [11 empty] | 5/29/2017 | Closed | OBS-TBA | 4 | 3/30/2017 |  | 60
000036508 | 21 | OSP-Obsolescence-PN 0026367-000 CABLE,KEYENCE,2M RCVR,PJ-VC2R | NGUYEN, TOANT | 1 | 0 | 0 | 2017-03-16 | 9 |  | 49 | [7 empty] | 9/23/2017 | Open | OBS | 118 | 3/7/2017 |  | 200
000036519 | 345 | OSP-Obsolescence-PN 0262225-000FRU KIT,PCB ASSY,TIMING GEN,SP1-TBI | LO, THANG | 5 | 5 | 12 | 2017-03-16 | 9 |  | 49 | [7 empty] | 7/25/2017 | Open | OBS | 118 | 3/7/2017 |  | 140 |  |  | Attention
000036520 | 91 | OSP-Obsolescence-PN 750-071923-000UN-INT PWR SUPPLY,120V,2200VA,KT 9XI | NGUYEN, TOANT | 3 | 1 | 4 | 2017-03-16 | 9 |  |  |  | 36 | 14 |  |  | 28 | 7 | 8/2/2017 | Open | OBS | 118 | 3/7/2017 |  | 148 |  |  | Need Update
000036783 | 4 | OSP-Obsolescence-PN 0219545-001 FRU KIT,PWR SUPPLY 5VDC 800AMPS 4KW | MAI, SON | 15 | 3 | 2.4 | [11 empty] | 6/7/2017 | Assigned | OBS-TBA | 17 | 4/7/2017 |  | 61
000036634 |  | OSP-MES-Fan assembly needs to be reverse engineered and documented | NGUYEN, HIEU | NA | NA | NA | [12 empty] | Open | MES | 103 | 3/22/2017
000036882 | 534 | OSP-Obsolescence-PN 0627529-000 PKG FRU ASSY,TSTD PS,IC,SLX | MAI, SON | 10 | 0 | 51.78 | [11 empty] | 6/18/2017 | Assigned | OBS-TBA | 10 | 4/18/2017 |  | 61
000036692 | 101 | OSP-Obsolescence-PN 752-688092-000 POWER SUPPLY,350 WATT | NGUYEN, BAO | 4 | 2 | 6 | 2017-04-07 | 8 | [9 empty] | 9/1/2017 | Open | OBS | 95 | 3/30/2017 |  | 155
000036901 | 51 | OSP-Obsolescence-PN 0249956-000 FRU KIT,PCA,MEASUREMENT CONTROL UV1050 | MAI, SON | 3 | 0 | 0 | [11 empty] | 6/19/2017 | Assigned | OBS-TBA | 9 | 4/19/2017 |  | 61
000036728 | 309 | OSP-Obsolescence-PN 095-386274-000CONTACTOR,AUXILIARY,1NO,FRONT | NGUYEN, HOANG | 1 | 1 | 12 | 2017-04-07 | 4 | DONE- short-term solution approved 5/2/2017 | 42 | 0 | 7 | 7 | -37 | 44 | 28 | 7 | 7/14/2017 | Open | OBS | 91 | 4/3/2017 |  | 102 |  |  | Need Update
000036903 | 124 | SMFG-Obsolescence-PN 0232670-000 ETHERNET SWTCH,DELL,1GB,48 PORT W/ BRKT | MAI, SON | 12 | 7 | 7 | [11 empty] | 6/19/2017 | Assigned | OBS-TBA | 9 | 4/19/2017 |  | 61
000036782 | 97 | OSP-Obsolescence-PN 0151400-000KIT,P/S REPL PN 070-032763-00 SWS152T | NGUYEN, TOANT | 10 | 4 | 4.8 | 2017-04-17 | 10 |  | 28 | [5 empty] | 61 | 7 | 12/7/2017 | Open | OBS | 87 | 4/7/2017 |  | 244
000036798 | 35 | OSP-Obsolescence-PN 070-774098-000 POWER SUPPLY,5V,750A,208VAC 3 PHASE | DUONG, TAM | 5 | 0 | 0 | 2017-04-16 | 6 | [9 empty] | 12/27/2017 | Open | OBS | 84 | 4/10/2017 |  | 261
000036884 | 71 | OSP-Obsolescence-PN 0050858-000 FRU,ASSY,FAN MTG PANEL | LO, THANG | 1 | 0 | 0 | 2017-05-03 | 15 | [9 empty] | 10/30/2017 | Open | OBS | 76 | 4/18/2017 |  | 195
000036902 | 76 | OSP-Obsolescence-PN 730-733811-001 CABLE,IMAGE SMB TO IMACS 3 | NGUYEN, TOANT | 1 | 0 | 0 |  |  | DONE- short-term solution approved 4/27 | [8 empty] | 8/7/2017 | Open | OBS | 75 | 4/19/2017 |  | 110
000036905 |  | KT Pro - BOM Comparison of SP1-TBI & SP1-DLS | NGUYEN, HIEU | NA | NA | NA | [12 empty] | Closed | KTPRO | 29 | 4/19/2017
000036912 |  | OSP-MES-IOT/ Electron Source Station | PHAN, AN | NA | NA | NA | [12 empty] | Open | MES | 74 | 4/20/2017 |  | 133
000036326 |  | DOC SUPPORT - PN 0652628-000 PKG FRU ASSY,MACBOX,SLX | NGUYEN, TOANT | NA | NA | NA | [11 empty] | 5/25/2017 | Closed | DOC | 75 | 2/17/2017 |  | 97
000036913 |  | OSP-MES-IOT/ Electron Source Station | NGUYEN, BAO | NA | NA | NA | [11 empty] | 7/30/2017 | Open | MES | 74 | 4/20/2017 |  | 101
000036959 |  | ODC-Scoping-Redesign-PN 0219545-001 FRU KIT,PWR SUPPLY 5VDC 800AMPS 4KW | NGUYEN, HIEU | NA | NA | NA | [12 empty] | Closed | ODC | 26 | 4/26/2017
000036670 |  | OSP-MES-IOT/ Electron Source Station | TRUONG, THI | NA | NA | NA | [12 empty] | Closed | MES | 36 | 3/28/2017
000036970 | 131 | OSP-Obsolescence-PN 0057977-001 PCB ASSY,CPU 200MHZ MMX,CONFIG,SFS6XX0 | MAI, SON | 21 | 0 | 9.14 | [11 empty] | 6/27/2017 | Assigned | OBS-TBA | 7 | 4/27/2017 |  | 61
000036971 | 44 | OSP-Obsolescence-PN 740-733720-000 ASSY,50/60HZ,IMPELLER,UI,CE,BLAZER | MAI, SON | 1 | 0 | 0 | [11 empty] | 6/27/2017 | Assigned | OBS-TBA | 7 | 4/27/2017 |  | 61
000036972 | 82 | OSP-Obsolescence-PN 0374108-000 ASSY,PDU,2365 | MAI, SON | 1 | 0 | 0 | [11 empty] | 6/27/2017 | Assigned | OBS-TBA | 7 | 4/27/2017 |  | 61
000037003 | 1144 | OSP-Obsolescence-PN 0000845-000 KIT,FRU,FIXED CASSETTE,300MM | MAI, SON | 0 | 0 | 999 | [11 empty] | 7/2/2017 | Assigned | OBS-TBA | 12 | 5/3/2017 |  | 60
000037004 | 110 | OSP-Obsolescence-PN 0260735-000 CBL ASSY,SWE PR CAM ND CTL W/FRT BEAD | MAI, SON | 2 | 1 | 6 | [11 empty] | 7/2/2017 | Assigned | OBS-TBA | 8 | 5/3/2017 |  | 60
000037022 |  | KTS-Transporter's PCAs test fixture | DUONG, TAM | NA | NA | NA | [12 empty] | Open | KTS | 56 | 5/8/2017
000037029 |  | ODC-AR Assignment tracker | NGUYEN, HOANG | NA | NA | NA | [12 empty] | Open | ODC | 56 | 5/8/2017
000037050 | 122 | OSP-Obsolescence-PN 209171 BLOWER 325CFM,230VAC,4 HOSE | NGUYEN, HOANG | 5 | 3 | 7.2 | [11 empty] | 7/8/2017 | Closed | OBS | 48 | 5/9/2017 |  | 60
000037057 |  | OSP-MES-1. To evaluate replacement power supply for 0219545-001;2. To compare the replacement power supplies with the existing model 0219545-0013. Implement the interface adapter, sensing wiring an | NGUYEN, HIEU | NA | NA | NA | [12 empty] | Open | MES | 55 | 5/9/2017
000036859 |  | OSP-FAI-PN 0667972-000 RETROFIT KIT,SCSI SE/DIFF CONV,GIGAPREP | NGUYEN, HIEU | NA | NA | NA | [12 empty] | Open | OBS | 77 | 4/17/2017
000037023 |  | KTS-Transporter's PCAs test fixture | NGUYEN, HIEU | NA | NA | NA | [12 empty] | Open | KTS | 56 | 5/8/2017
000037024 |  | KTS-Transporter's PCAs test fixture | NGUYEN, BAO | NA | NA | NA | [12 empty] | Open | KTS | 56 | 5/8/2017
000037076 | 18 | OSP-Obsolescence-PN 131-07706-000 CHAIN,FLEX CABLE | MAI, SON | 1 | 0 | 0 | [11 empty] | 7/11/2017 | Assigned | OBS-TBA | 10 | 5/12/2017 |  | 60
000037077 | 39 | OSP-Obsolescence-PN 0569769-000 FRU,SYS TSTD,MOTOR AMP ASSY,ES35 | NGUYEN, HIEU | 1 | 0 | 0 | [11 empty] | 7/11/2017 | Open | OBS | 52 | 5/12/2017 |  | 60
000037079 | 69 | OSP-Obsolescence-PN 730-371061-000 ASSY,SLX,SAC DRIVER,BP TO STEPPER B/H | LO, THANG | 2 | 0 | 0 | 2017-05-19 | [10 empty] | 11/14/2017 | Open | OBS | 52 | 5/12/2017 |  | 186
000037124 |  | ODC-CAE, focusing on Computational Fluid Dynamics, investigation | PHAN, AN | NA | NA | NA | [12 empty] | Open | ODC | 48 | 5/16/2017
000037132 |  | KTS-PN 0276654-001 FRU ASSY,TSTD PS M31 HOST/NODE | NGUYEN, HIEU | NA | NA | NA | [12 empty] | Closure Requested | KTS | 47 | 5/17/2017
000037144 | 120 | OSP-Obsolescence-PN 0092083-001 KIT UPGRD,PILLAR,SST WTR FTG,AITUV | MAI, SON | 4 | 3 | 9 | [11 empty] | 7/16/2017 | Assigned | OBS-TBA | 7 | 5/17/2017 |  | 60
000037162 |  | switch PN 0002066-000 & header PN 0002156-000 are EOL, need replacements... used in cable assembly 0001011-002 which in turn is used in assy P/N 0000845-000 | LO, THANG | NA | NA | NA | [12 empty] | Closed | MES | 35 | 5/18/2017
000037174 |  | OSP - FAI for KT # 0020042-000, CBL ASSY,STRT/STP/EMO,SP1 DLS | NGUYEN, HIEU | NA | NA | NA | [12 empty] | Open | FAI | 42 | 5/22/2017
000037175 |  | P1 order # 10654932 for KT # 730-333386-000, ASSY,WIRED MOTOR,SAC,COLL,SLX | NGUYEN, HIEU | NA | NA | NA | [12 empty] | Closed | ESC | 17 | 5/22/2017
000037181 | 812 | OSP-Obsolescence-PN 51-0179 STAGE ASSY,SHUTTLE,HANDLER | MAI, SON | 1 | 1 | 200 | [11 empty] | 7/22/2017 | Closed | OBS-TBA | 30 | 5/23/2017 |  | 60
000037182 | 797 | SMFG-Obsolescence-PN 0128546-000 ASSY,FRU,CRATED,IC,PUMA 9000,DELUXE | MAI, SON | 1 | 0 | 188 | [11 empty] | 7/22/2017 | Open | OBS | 41 | 5/23/2017 |  | 60
000037185 | 107 | OSP-Obsolescence-PN 0357521-000 KIT,MONITOR 17 | NGUYEN, HOANG | 2 | 1 | 6 | [11 empty] | 7/22/2017 | Open | OBS | 41 | 5/23/2017 |  | 60
000037234 |  | MES-PN 780-14105-002 KIT,SHIPG,ASSY,CHASS,FCB,LAW PROTECT | NGUYEN, HIEU | NA | NA | NA | [12 empty] | Closed | MES | 17 | 5/29/2017
000037240 | 90 | OSP-Obsolescence-PN 0068036-000 DIODE,1W,355NM,SS | MAI, SON | 4 | 1 | 3 | [11 empty] | 7/28/2017 | Assigned | OBS-TBA | 10 | 5/29/2017 |  | 60
000037311 | 37 | OSP-Obsolescence-PN 710-657952-20 ASSY,TESTED THETA EDGE LAMP PCB (4" SYS) | NGUYEN, TOANT | 2 | 0 | 0 | [11 empty] | 8/7/2017 | Open | OBS | 26 | 6/7/2017 |  | 61
000037383 | 14 | OSP-Obsolescence-PN 0250491-002 RETROFIT KIT,17 INCH LCD MONITOR | NGUYEN, HOANG | 19 | 12 | 7.58 | [11 empty] | 8/15/2017 | Open | OBS | 18 | 6/15/2017 |  | 61
000037384 | 20 | OSP-Obsolescence-PN 0158721-000 PWR SPLY, MOD, 1U, 230V X 12 | LO, THANG | 2 | 0 | 0 | [11 empty] | 8/15/2017 | Open | OBS | 18 | 6/15/2017 |  | 61
000037385 | 63 | OSP-Obsolescence-PN 55-0558-02 CBL ASSY,SVO CRD-SYS INTFC,J11 | NGUYEN, HOANG | 1 | 0 | 0 | [11 empty] | 8/15/2017 | Open | OBS | 18 | 6/15/2017 |  | 61
000037387 | 78 | OSP-Obsolescence-PN 210-07949-000 VALVE,RIGHT ANGLE,NW 16 MANUAL | LO, THANG | 1 | 0 | 0 | [11 empty] | 8/15/2017 | Open | OBS | 18 | 6/15/2017 |  | 61
000037388 | 120 | OSP-Obsolescence-PN 0002062-000 ASSY,ENCL,UNIV.DC PWR SPLY | NGUYEN, TOANT | 7 | 4 | 6.86 | [11 empty] | 8/15/2017 | Open | OBS | 18 | 6/15/2017 |  | 61
000037400 | 41 | SMFG-Obsolescence-PN 760-321660-003 ASSY,SPATIAL FILTER/PRESCANNER | MAI, SON | 2 | 0 | 0 | [11 empty] | 8/16/2017 | Open | OBS | 17 | 6/16/2017 |  | 61
000037401 | 548 | OSP-Obsolescence-PN 0057209-000 ASYST AXYS,VAC HNDLG VAC MANIFOLD | MAI, SON | 3 | 0 | 57.54 | [11 empty] | 8/16/2017 | Assigned | OBS-TBA | 6 | 6/16/2017 |  | 61
000035708 | 538 | OSP-Obsolescence-PN 501972 CBL ASSY,8 SERIAL PORTS,AIT2 | NGUYEN, TOANT | 1 | 4 | 48 | 2016-11-30 | 2 | [9 empty] | 5/12/2017 | Closed | OBS | 203 | 11/28/2016 |  | 165 | Cable
000037440 | 2 | SMFG-Obsolescence-PN 780-391907-000 KIT,SLX +5V POWER SYSTEM RETROFIT | MAI, SON | 13 | 1 | 0.92 | [11 empty] | 8/21/2017 | Open | OBS-TBA | 12 | 6/21/2017 |  | 61
000037442 | 796 | SMFG-Obsolescence-PN 0586375-000 PKG FRU,CHASSIS,IC,CPCI RAPIDIO,W/O H | MAI, SON | 1 | 0 | 188 | [11 empty] | 8/21/2017 | Open | OBS-TBA | 12 | 6/21/2017 |  | 61
000037445 | 67 | OSP-Obsolescence-PN 11301397270000 BACKSIDE INIT ROT DISTRIBUTOR | MAI, SON | 2 | 0 | 0 | [11 empty] | 8/21/2017 | Open | OBS-TBA | 12 | 6/21/2017 |  | 61
000037448 | 125 | OSP-Obsolescence-PN 0054603-000 TESTED COMPUTER,23XX IPC,WINDOWS 2000 OS | MAI, SON | 6 | 0 | 8 | [11 empty] | 8/21/2017 | Open | OBS-TBA | 12 | 6/21/2017 |  | 61
000037452 |  | OSP-FAI-KT# 750-032992-00, CARD CAGE 6U/84HP X 160/220MM 12 SLOT | NGUYEN, HIEU | NA | NA | NA | [12 empty] | Open | FAI | 12 | 6/21/2017
000037529 | 123 | OSP-Obsolescence-PN 0062496-001 ASSY,F.O,CH0-7,IMG CMP.TO I/O PNL(CIBO) | MAI, SON | 3 | 2 | 8 | [11 empty] | 8/29/2017 | Open | OBS-TBA | 4 | 6/29/2017 |  | 61
000037549 |  | P2 order # 10663057 for KT # 705-369707-000, PCB,SCSI DISCNCT,INLINE SINGLE/DIFF CONV | NGUYEN, HIEU | NA | NA | NA | [12 empty] | Open |  | 3 | 6/30/2017

## Categorize
ENG-RVW version | 0
AR_Report version | 0
ARID | Problem statement | Elec | Mech | PC | Software | Opt
000033018 | OSP - MES - KT# 750-032992-00, CARD CAGE 6U/84HP X 160/220MM 12 SLOT
000036883 | OSP-Obsolescence-PN 710-659411-001 ASSY,TESTED RANDTESCAN UP4
000033949 | OSP-Obsolescence-PN 0384073-000 TSTD PCA,LVD-LGHTNG VID DIAG V2,SLX
000036857 | OSP-MES-IOT/ Electron Source Station
000034094 | OSP-Obsolescence-PN 730-371063-000 CABLE,SLX,LOCO DRIVER,BP TO STEPPER B/H
000034381 | OSP-Obsolescence-PN 705-369707-000 PCB,SCSI DISCNCT,INLINE SINGLE/DIFF CONV
000034523 | OSP-Obsolescence-PN 730-371065-000 ASSY,SLX,PRISM DRIVER,BP TO STEPPER B/H
000034587 | OSP-CIP- I.o.T / Electron Source Station
000034721 | OSP-Obsolescence-PN 0256402-000 UN-INT,POWER SUPPLY,120V,KLA 9X
000034726 | OSP-Obsolescence-PN 0133120-000 KIT,LCD MONITOR UPG,17" |  |  | 1
000034412 | OSP-Obsolescence-PN 0532282-000 DRIVE,3.5IN,4TB,7.2K,SAS,6GBPS |  |  | 1
000034410 | OSP-Obsolescence-PN 0261867-000 UN-INT PWR SUPPLY,100V,3000VA,KT 9XI | 1
000035063 | SMFG-Obsolescence-PN 0389022-000 ASSY, TSTD, HD, UIC10 |  |  | 1
000035444 | OSP-MES-IOT/ Electron Source Station | 1 |  |  | 1
000034941 | OSP-Obsolescence-PN 720-17868-000 ASSY,DONGLE,NT,VARS |  |  | 1
000035512 | MES - Creating a wiring diagram for new MACBOX 0634283-000
000035088 | OSP-Obsolescence-PN 0265735-000 250G, SATA DISK, OP CONSOLE, 6XX |  |  | 1
000034863 | OSP-Obsolescence-PN 0569769-000 FRU,SYS TSTD,MOTOR AMP ASSY,ES35 | 1
000034794 | OSP-Obsolescence-PN 0222301-001 FRU,EMI NOISE CANCELLATION UNIT,eS35 | 1
000035556 | SMFG-Obsolescence-PN 0081663-005 KIT,FRU,COMPUTER & ACCESSORIES,ECD-2 |  |  | 1
000035109 | SMFG-Obsolescence-PN 740-689343-000 ASSY,RIGHT CASSETTE NEST XP |  | 1
000035627 | SMFG-Obsolescence-PN 780-17407-000 KIT,CONTROLLER,DUAL ION PUMP,8XXX | 1
000035709 | OSP-Obsolescence-PN 0205550-000 ASSY,PCB,ATSB,199DEG | 1
000035743 | SMFG-Obsolescence-PN 0308014-001 PKG FRU,SHUTTER ASSY,WAFER,SP1-TBI | 1
000035515 | OSP-Obsolescence-PN 760-034988-00 ASSY,CHIRP CELL CYL LENS FIELD STOP |  | 1
000035817 | OSP-Obsolescence-PN 780-14105-002 KIT,SHIPG,ASSY,CHASS,FCB,LAW PROTECT | 0
000035377 | OSP-Obsolescence-PN 229-00775-002 TUB'G,PE .170 ID X 1/4 OD BLK | 1
000035630 | OSP-Obsolescence-PN 0033120-001 PCB,FRU,SYSTEM CONTROLLER 2 | 1
000035629 | SMFG-Obsolescence-PN 0035650-000 EHEE ASSY,SNGL 300MM FOUP,SP1-EHII | 0
000035873 | SMFG-Obsolescence-PN 0030686-000 DUAL 200MM EHEE ASSY,EHII,SP1-TBI | 0
000036090 | OSP-Obsolescence-PN 0212590-000 DRIVE,USB,500Gb Maxtor OneTouch III | 1
000036036 | ODC-Managing ODC OBS AR's and sustaining team. |  |  | 1
000036421 | OSP-Obsolescence-PN 810-01591-000 ASSY,CABLE,H/V ELECT SRCE | 0
000036363 | OSP-Obsolescence-PN 740-372671-000 PKG DSK,RAW,WIDE SCSI,36GB,GIGAPREP SWAP | 1
000036134 | OSP-MES-ODC onsite support | 0
000036444 | OSP-Obsolescence-PN 750-344623-000PCB,SERVO AMPLIFIER,MOTOR | 0
000036445 | OSP-Obsolescence-PN 0034984-001SET,HUBPORT,USB,7 PORT,W/POWER SUPPLY | 0
000036160 | OSP-Obsolescence-PN 350184 BRG,LINEAR,THK,2RSR9+155L |  |  | 1
000036270 | OSP-Obsolescence-PN 0614200-000 FRU KIT,17 INCH LCD,ASET-F5 |  | 1
000036516 | SMFG-Obsolescence-PN 784-056013-001 FRU QIC 150 TAPE DRIVE W/PS |  |  | 1
000036442 | OSP-Obsolescence-PN 0140589-000G, COPPER PASS-THRU I/O MODULE |  |  | 1
000036503 | OSP-Obsolescence-PN 0026366-000 CABLE,KEYENCE,2M TRMTR,PJ-VC2T |  |  | 1
000036440 | OSP-Obsolescence-PN 750-381989-000DISK ARRAY,SUN T3,1X9X73G | 1
000036590 | OSP-Obsolescence-PN 0081663-007 KIT,FRU,COMPUTER & ACCESSORIES,ECD-2 |  |  | 0
000036299 | SMFG-Obsolescence-PN 0044208-000KIT, UPGRADE, H2 VL-586 CPU |  |  | 1
000036364 | OSP-Obsolescence-PN 0152723-000 AMPLFR,TRCK,COPLEY,FRU | 0
000036510 | OSP-Obsolescence-PN 0089335-004 ASSY,INTERLOCK BOX,PHNX | 0
000036423 | OSP-Obsolescence-PN 470-40158-000 COMPUTER, DELL 2600 FILE SERVER, RANGER | 0
000036630 | OSP-Obsolescence-PN 065-380208-000CAP PROX SENSOR,10-65VDC,DUAL CONTACTS | 0
000036631 | OSP-Obsolescence-PN 291-19824-000 SYSTEM WAFER,200MM,W/CONTAINER | 0
000036462 | OSP-Obsolescence-PN 0335949-000 INDEXER,V1,SMIF | 0
000036511 | OSP-Obsolescence-PN 0604782-000 FRU,ASSY,TDI ELECTRONICS,HDD+ | 0
000036512 | SMFG-Obsolescence-PN 740-652341-00 ASSY ELEVATOR | 0
000036394 | OSP-Obsolescence-PN 0032227-000 MAPPER, HAMA, 7" CABLE W 4 PIN CONN | 0
000036690 | OSP-Obsolescence-PN 54-0297 PCA,SERVO FUSE ADAPTER | 0
000036508 | OSP-Obsolescence-PN 0026367-000 CABLE,KEYENCE,2M RCVR,PJ-VC2R | 0
000036519 | OSP-Obsolescence-PN 0262225-000FRU KIT,PCB ASSY,TIMING GEN,SP1-TBI | 1
000036520 | OSP-Obsolescence-PN 750-071923-000UN-INT PWR SUPPLY,120V,2200VA,KT 9XI | 1
000036783 | OSP-Obsolescence-PN 0219545-001 FRU KIT,PWR SUPPLY 5VDC 800AMPS 4KW | 1
000036634 | OSP-MES-Fan assembly needs to be reverse engineered and documented | 1
000036882 | OSP-Obsolescence-PN 0627529-000 PKG FRU ASSY,TSTD PS,IC,SLX |  | 1
000036692 | OSP-Obsolescence-PN 752-688092-000 POWER SUPPLY,350 WATT | 0
000036901 | OSP-Obsolescence-PN 0249956-000 FRU KIT,PCA,MEASUREMENT CONTROL UV1050 | 1
000036728 | OSP-Obsolescence-PN 095-386274-000CONTACTOR,AUXILIARY,1NO,FRONT | 0
000036903 | SMFG-Obsolescence-PN 0232670-000 ETHERNET SWTCH,DELL,1GB,48 PORT W/ BRKT | 1
000036782 | OSP-Obsolescence-PN 0151400-000KIT,P/S REPL PN 070-032763-00 SWS152T | 0
000036798 | OSP-Obsolescence-PN 070-774098-000 POWER SUPPLY,5V,750A,208VAC 3 PHASE | 1
000036884 | OSP-Obsolescence-PN 0050858-000 FRU,ASSY,FAN MTG PANEL | 1
000036902 | OSP-Obsolescence-PN 730-733811-001 CABLE,IMAGE SMB TO IMACS 3 |  | 1
000036905 | KT Pro - BOM Comparison of SP1-TBI & SP1-DLS | 1
000036912 | OSP-MES-IOT/ Electron Source Station | 0
000036326 | DOC SUPPORT - PN 0652628-000 PKG FRU ASSY,MACBOX,SLX | 1 |  |  | 1
000036913 | OSP-MES-IOT/ Electron Source Station
000036959 | ODC-Scoping-Redesign-PN 0219545-001 FRU KIT,PWR SUPPLY 5VDC 800AMPS 4KW | 1 |  |  | 1
000036670 | OSP-MES-IOT/ Electron Source Station | 1
000036970 | OSP-Obsolescence-PN 0057977-001 PCB ASSY,CPU 200MHZ MMX,CONFIG,SFS6XX0 | 1 |  |  | 1
000036971 | OSP-Obsolescence-PN 740-733720-000 ASSY,50/60HZ,IMPELLER,UI,CE,BLAZER | 0 |  |  |  |  | Count | EE | ME | PC | SW | OE
000036972 | OSP-Obsolescence-PN 0374108-000 ASSY,PDU,2365 | 0 |  |  |  |  | 88 | 30 | 9 | 13 | 4
000037003 | OSP-Obsolescence-PN 0000845-000 KIT,FRU,FIXED CASSETTE,300MM | 0 |  |  |  |  | Percentage | 34.0909 | 10.2273 | 14.7727 | 4.5455
000037004 | OSP-Obsolescence-PN 0260735-000 CBL ASSY,SWE PR CAM ND CTL W/FRT BEAD | 0
000037022 | KTS-Transporter's PCAs test fixture | 0
000037029 | ODC-AR Assignment tracker | 1 | 1 | 1
000037050 | OSP-Obsolescence-PN 209171 BLOWER 325CFM,230VAC,4 HOSE
000037057 | OSP-MES-1. To evaluate replacement power supply for 0219545-001;2. To compare the replacement power supplies with the existing model 0219545-0013. Implement the interface adapter, sensing wiring an |  | 1
000036859 | OSP-FAI-PN 0667972-000 RETROFIT KIT,SCSI SE/DIFF CONV,GIGAPREP | 1
000037023 | KTS-Transporter's PCAs test fixture | 1
000037024 | KTS-Transporter's PCAs test fixture | 1 | 1
000037076 | OSP-Obsolescence-PN 131-07706-000 CHAIN,FLEX CABLE | 1 | 1
#REF! | #REF!
000037077 | OSP-Obsolescence-PN 0569769-000 FRU,SYS TSTD,MOTOR AMP ASSY,ES35
000037079 | OSP-Obsolescence-PN 730-371061-000 ASSY,SLX,SAC DRIVER,BP TO STEPPER B/H
000037124 | ODC-CAE, focusing on Computational Fluid Dynamics, investigation
#REF! | #REF!
000037132 | KTS-PN 0276654-001 FRU ASSY,TSTD PS M31 HOST/NODE
000037144 | OSP-Obsolescence-PN 0092083-001 KIT UPGRD,PILLAR,SST WTR FTG,AITUV
000037162 | switch PN 0002066-000 & header PN 0002156-000 are EOL, need replacements... used in cable assembly 0001011-002 which in turn is used in assy P/N 0000845-000
#REF! | #REF!
000037174 | OSP - FAI for KT # 0020042-000, CBL ASSY,STRT/STP/EMO,SP1 DLS
#REF! | #REF!
000037175 | P1 order # 10654932 for KT # 730-333386-000, ASSY,WIRED MOTOR,SAC,COLL,SLX
000037181 | OSP-Obsolescence-PN 51-0179 STAGE ASSY,SHUTTLE,HANDLER
000037182 | SMFG-Obsolescence-PN 0128546-000 ASSY,FRU,CRATED,IC,PUMA 9000,DELUXE
000037185 | OSP-Obsolescence-PN 0357521-000 KIT,MONITOR 17
000037234 | MES-PN 780-14105-002 KIT,SHIPG,ASSY,CHASS,FCB,LAW PROTECT
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
000037240 | OSP-Obsolescence-PN 0068036-000 DIODE,1W,355NM,SS
000037311 | OSP-Obsolescence-PN 710-657952-20 ASSY,TESTED THETA EDGE LAMP PCB (4" SYS)
#REF! | #REF!
000037383 | OSP-Obsolescence-PN 0250491-002 RETROFIT KIT,17 INCH LCD MONITOR
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
000037384 | OSP-Obsolescence-PN 0158721-000 PWR SPLY, MOD, 1U, 230V X 12
000037385 | OSP-Obsolescence-PN 55-0558-02 CBL ASSY,SVO CRD-SYS INTFC,J11
000037387 | OSP-Obsolescence-PN 210-07949-000 VALVE,RIGHT ANGLE,NW 16 MANUAL
000037388 | OSP-Obsolescence-PN 0002062-000 ASSY,ENCL,UNIV.DC PWR SPLY
000037400 | SMFG-Obsolescence-PN 760-321660-003 ASSY,SPATIAL FILTER/PRESCANNER
000037401 | OSP-Obsolescence-PN 0057209-000 ASYST AXYS,VAC HNDLG VAC MANIFOLD
000035708 | OSP-Obsolescence-PN 501972 CBL ASSY,8 SERIAL PORTS,AIT2
#REF! | #REF!
000037440 | SMFG-Obsolescence-PN 780-391907-000 KIT,SLX +5V POWER SYSTEM RETROFIT
000037442 | SMFG-Obsolescence-PN 0586375-000 PKG FRU,CHASSIS,IC,CPCI RAPIDIO,W/O H
000037445 | OSP-Obsolescence-PN 11301397270000 BACKSIDE INIT ROT DISTRIBUTOR
000037448 | OSP-Obsolescence-PN 0054603-000 TESTED COMPUTER,23XX IPC,WINDOWS 2000 OS
000037452 | OSP-FAI-KT# 750-032992-00, CARD CAGE 6U/84HP X 160/220MM 12 SLOT
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
000037529 | OSP-Obsolescence-PN 0062496-001 ASSY,F.O,CH0-7,IMG CMP.TO I/O PNL(CIBO)
000037549 | P2 order # 10663057 for KT # 705-369707-000, PCB,SCSI DISCNCT,INLINE SINGLE/DIFF CONV
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## AR in 2016
ARID | Problem statement | Elec | Mech | PC | Software | Opt
000032561 | OSP-Obsolescence-PN 0045696-000 FRAME,SCSI,68 PIN TO SCA 80 PIN | 1 |  |  |  |  | Count | EE | ME | PC | SW | OE
000032882 | OSP-Obsolescence-PN 0021844-000 KEYBOARD SUBASSY,DROP IN, DLS |  |  | 1 |  |  | 36 | 22 | 1 | 12 | 1 | 0
000033059 | OSP-Obsolescence-PN 0136044-000 PWR SUPPLY ATX 300W | 1
000033097 | OSP-Obsolescence-PN 0243007-000 ASSY,DVD DRIVE FOR SUN FIRE V440,5XX |  |  | 1
000033228 | OSP-Obsolescence-PN 0141462-000 MONITOR,LCD,20",1600X1200,BLK,ROHS/WEEE |  |  | 1
000033489 | OSP-Obsolescence-PN 0237300-000 KEYBOARD,CLASSIC 200,USB |  |  | 1
000033506 | OSP-Obsolescence-PN 575-670748-000 AIR CYLINDER,RECTANGULAR,.78 STROKE |  | 1
000033813 | OSP-Obsolescence-PN 0310630-000 FRU KIT,ASSY,MINI KEYBOARD,LABEL,SP1 |  |  | 1
000033815 | OSP-Obsolescence-PN 379476 MOTOR,DCR,SVC RPL,SP1 | 1
000033833 | OSP-Obsolescence-PN 730-071848-000 CBL,SCSI,LONG CONN TO SCSICARD VIA CD&TD | 1
000033861 | OSP-Obsolescence-PN 0098340-000 FRU, LAMP HOUSING, 243X | 1
000033949 | OSP-Obsolescence-PN 0384073-000 TSTD PCA,LVD-LGHTNG VID DIAG V2,SLX | 1
000034001 | OSP-Obsolescence-PN 730-325067-006 CABLE,IAS,INTLK TO N2 FLOW,5XX | 1
000034046 | OSP-Obsolescence-PN 0295639-000 MONITOR,17"LCD,1U RACK MNT |  |  | 1
000034052 | OSP-Obsolescence-PN 780-688028-000 ASSY,FRU,X STAGE,2135,CE | 1
000034057 | OSP-Obsolescence-PN 750-381972-000 KEYBOARD,SUN,SUN TYPE 6,USB |  |  | 1
000034080 | OSP-Obsolescence-PN 15-0110 FIRMWARE,SET,SBC PCA,V4.00 |  |  |  | 1
000034094 | OSP-Obsolescence-PN 730-371063-000 CABLE,SLX,LOCO DRIVER,BP TO STEPPER B/H | 1
000034126 | OSP-Obsolescence-PN 0035528-000 PCB ASSY,ROBOT DISTR,AIT UV | 1
000034176 | OSP-Obsolescence-PN 730-733877-000 CABLE,SCSI 2,PC TO MO/JAZ DRIVES | 1
000034381 | OSP-Obsolescence-PN 705-369707-000 PCB,SCSI DISCNCT,INLINE SINGLE/DIFF CONV | 1
000034383 | OSP-Obsolescence-PN 38-0144 SCSI ADPTRSCSI.3(EXT)MTOIDCSOM | 1
000034384 | OSP-Obsolescence-PN 147222 PWR SUPPLY,12V4.2A,SINGL OUT | 1
000034410 | OSP-Obsolescence-PN 0261867-000 UN-INT PWR SUPPLY,100V,3000VA,KT 9XI | 1
000034412 | OSP-Obsolescence-PN 0532282-000 DRIVE,3.5IN,4TB,7.2K,SAS,6GBPS |  |  | 1
000034509 | OSP-Obsolescence-PN 0095545-000 CBL ASSY,23XX INTLOCK/EMO/24VDC PHOENIX | 1
000034521 | OSP-Obsolescence-PN 0202771-000 ASSY,KVM SWITCH E-SERIES | 1
000034523 | OSP-Obsolescence-PN 730-371065-000 ASSY,SLX,PRISM DRIVER,BP TO STEPPER B/H | 1
000034550 | OSP-Obsolescence-PN 0137211-000 ASSY,I/O MASTER,OPEN LOADER,PHOENIX | 1
000034726 | OSP-Obsolescence-PN 0133120-000 KIT,LCD MONITOR UPG,17" |  |  | 1
000034794 | OSP-Obsolescence-PN 0222301-001 FRU,EMI NOISE CANCELLATION UNIT,eS35 | 1
000034941 | OSP-Obsolescence-PN 720-17868-000 ASSY,DONGLE,NT,VARS |  |  | 1
000035103 | OSP-Obsolescence-PN 0064166-000 MONITOR, UPPER, UI 15" FLAT PANEL |  |  | 1
000035106 | OSP-Obsolescence-PN 0281806-000 COMBO,KEYBRD/MOUSE,OPTICAL,PS2,WIRED,BLK |  |  | 1
000035107 | OSP-Obsolescence-PN 0333087-000 PWR SPLY ASSY,+/-5V,3A,LINEAR | 1
000035109 | SMFG-Obsolescence-PN 740-689343-000 ASSY,RIGHT CASSETTE NEST XP | 1
000035339